## Project Plan
DA Portal - Project Plan
ID |  | Task | Priority | Predecessor | Status | Story ID | Estimated Hours | Actual Hours | Estimated Start Date | Estimated End Date | Actual Start Date | Actual End Date
1 | Architecture | System Design and Architecture
1.1 |  | High-level system design |  |  | In-progress
1.2 |  | Database Design |  |  | In-progress
1.3 |  | Low-level system design
1.4 |  | Deployment design |  |  | In-progress
Framework Development
|  | Core components – Base interfaces and services |  |  | In-progress
|  | Logging component |  |  | In-progress
|  | Security services component |  |  | In-progress
|  | Authentication and Authorization |  |  | In-progress
2 |  | UI Design & Component development
2.1 | All Users | Home/Login page |  |  | In-progress |  | 2
3 | Quality Manager | Dashboard |  |  |  |  | 5
3.1 |  | Drill-down operation
3.1.1 |  | List of scheduled reviews for the day/month |  |  |  |  | 3
3.1.2 |  | List of completed reviews for the day/month |  |  |  |  | 3
3.1.3 |  | List of rescheduled reviews for the day/month |  |  |  |  | 3
3.1.4 |  | List of cancelled reviews for the month |  |  |  |  | 3
3.1.5 |  | List of in-progress reviews for the day |  |  |  |  | 3
3.2 |  | List of reviews (Filter by reviewer, date, month, review type) |  | 3.1 |  |  | 3
3.3 |  | Project Master
3.3.1 |  | Create, Read, Update and Delete projects |  |  | UI Completed |  | 4
3.3.2 |  | Upload Project Master from Excel |  |  | UI Completed |  | 1
3.4 |  | Manage Reviewers
3.4.1 |  | Create, Read, Update and Delete reviewers |  |  | UI Completed |  | 4
3.5 |  | Plan Reviews
3.5.1 |  | Plan preparation and Validation |  |  | In-progress |  | 8
3.5.2 |  | Publish Plan |  |  | In-progress |  | 2
3.5.3 |  | Schedule Reviews |  | 3.5.2 | In-progress
3.5.3.1 |  | Creation of email templates |  |  | In-progress |  | 3
3.6 |  | Manage Reviews
3.6.1 |  | Cancel Reviews |  |  |  |  | 1
3.6.2 |  | Reschedule Reviews |  |  |  |  | 1
3.6.3 |  | Schedule Reviews |  |  |  |  | 1
3.6.4 |  | Send Reminders |  |  |  |  | 1
3.7 |  | Review/Moderate and Publish Reports |  |  |  |  | 3
3.8 |  | Create/Update Reports |  |  |  |  | 3
4 | Reviewer | Dashboard |  |  |  |  | 4
5 |  | View Scheduled reviews |  |  |  |  | 2
6 |  | Mark review as complete |  |  |  |  | 1
7 |  | Request to reschedule review |  |  |  |  | 2
8 |  | Request to cancel review |  |  |  |  | 2
9 |  | Create/Update Reports
10 | Managers (PM, DM, OPM, AM, CP, DP) | Dashboard |  |  |  |  | 4
11 |  | View Risks Identified by Reviews |  |  |  |  | 2
12 |  | Create, Read, Update and Delete Risks |  |  |  |  | 4
13 |  | Creation of Risks email templates |  |  |  |  | 3
14 | Reviewee | Dashboard |  |  |  |  | 4
15 |  | View risks raised by review type |  |  |  |  | 2
16 |  | Update Risk status |  |  |  |  | 2